## Raw Data
Project Name:
My Project
This unlicensed template has limited function. Execution, Control and Close data cannot be changed. You are free to unlock and modify licensed versions of these templates. See www.cvr-it.com for licensing information.
Reporting Periods: |  | 7/05 | 8/05 | 9/05 | 10/05 | 11/05 | 12/05 | 1/06 | 2/06 | 3/06 | 4/06 | 5/06 | 6/06 | 7/06 | 8/06 | 9/06 | 10/06 | 11/06 | 12/06 | 1/07 | 2/07 | 3/07 | 4/07 | 5/07 | 6/07
<==== Planned Costs per Reporting Period ====>
Planned Phase Costs
Initiation | 40000 | 5000 | 5000 | 10000 | 20000 | [20 empty] | 40000
Planning | 160000 |  |  |  |  | 20000 | 30000 | 50000 | 40000 | 20000 | [15 empty] | 160000
Execution | 650000 | [8 empty] | 30000 | 40000 | 50000 | 60000 | 60000 | 70000 | 80000 | 90000 | 80000 | 40000 | 30000 | 20000 |  |  |  |  | 650000
Control | 148000 | 2000 | 2000 | 2000 | 2000 | 4000 | 4000 | 8000 | 8000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 11000 | 8000 | 3000 | 2000 | 1000 | 1000 | 148000
Close | 24000 | [20 empty] | 10000 | 6000 | 4000 | 4000 | 24000
Project Total Planned Cost: |  |  | 1022000 |  |  | Time unit of project: |  | Months
Budgeted Cost per Reporting Period: |  | 7000 | 7000 | 12000 | 22000 | 24000 | 34000 | 58000 | 48000 | 59000 | 49000 | 59000 | 69000 | 69000 | 79000 | 89000 | 99000 | 89000 | 49000 | 41000 | 28000 | 13000 | 8000 | 5000 | 5000
Cumulative Plan Cost: |  | 7000 | 14000 | 26000 | 48000 | 72000 | 106000 | 164000 | 212000 | 271000 | 320000 | 379000 | 448000 | 517000 | 596000 | 685000 | 784000 | 873000 | 922000 | 963000 | 991000 | 1004000 | 1012000 | 1017000 | 1022000
Actual Cost: |  | 6300 | 6800 | 11400 | 23000 | 25000 | 22300 | 41000 | 49000 | 77000 | 55000 | 56000 | 78000 | 87000 | 88000 | 94000 | 94000 | 94000 | 44000 | 38000 | 22000 | 9000 | 8500 | 5300 | 4800
Cumulative Actual Cost: |  | 6300 | 13100 | 24500 | 47500 | 72500 | 94800 | 135800 | 184800 | 261800 | 316800 | 372800 | 450800 | 537800 | 625800 | 719800 | 813800 | 907800 | 951800 | 989800 | 1011800 | 1020800 | 1029300 | 1034600 | 1039400
Instructions:
Before you enter any data, do the following:
- Determine the total cost of each project phase
- Determine the number of reporting periods that each project phase will last (e.g. 3 months)
- Determine (or guestimate) the dollar cost that will occur during each reporting period for each phase
To enter planned project values (note: all data entry cells are white):
1. Enter project name in the space provided
2. Enter reporting periods in cells D4 through AA4 (e.g. weeks, months or quarters as dates (shown) or month1, month2, etc.)
3. Enter cost of each project phase under Planned Phase Costs
4. Enter the phase cost planned for each Reporting Period in the white cells provided. (see Initiation and Planning for an example of how this is done). Leave unused cells blank.
Cells in column AB will be red until the total cost for all reporting periods in a phase equals the project phase cost.
5. Enter time unit of the project. This is "Months" in the example. This is used as a label on the chart.
6. Planned cost per reporting period display in the 'Budgeted Cost per Reporting Period" line
7. Planned Cumulative Cost displays in the "Cumulative Planned Cost" line
8. Enter Actual Costs per reporting period as the data become available. The cumulative actual cost will display in the
Cumulative Actual Cost line. It is normal for the last correct cumulative cost figure to repeat through all succeeding months. Do NOT delete these numbers!
9. Modify the graph in the Cumulative Cost Curve tab as explained on that sheet
When should you use this template:
- Use this template when you need a Cumulative Cost Curve and you have a good idea of how your costs will be broken
out over the course of your project.
- This template is useful for projects that last between 4 and 24 reporting periods and where dollar estimates of cost per reporting period are available.
- See companion document "CumulativeCostCurve_Dollars_SampleData.xls" to see what a completed project looks like.

## Cumulative Cost Curve
Initial Setup
Once you have entered all of your Planned data in the Raw Data tab, do the following:
- Click once on the chart to select it and then click Chart on the toolbar
- Click Source Data and then Series
- Click Budgeted Cost and then in the Values box change "Raw data" to inlcude only the columns in which you have entered planning data.
For example, if your project will last 12 months you will have planned data in columns D through O, so the value for Raw Data should
be ='Raw Data'!$D$26:$O$26
Adding Actual Cost Data
As you add Actual Cost values, click once on the chart and then click Chart on the toolbar
- Click Source Data and then Series
- Click Actual Cost and then in the Values box change "Raw data" to inlcude the latest column in which you have Actual Cost data. In this -
the example we have Actual data for 3 months, so the last Actual data is in Column F. The value for Raw Data should
be ='Raw Data'!$D$30:$F$30
Note: this chart is easily added to a Word document. Just click on the chart, right click and Copy, then Paste into the Word document.

## Instructions
Raw Data Tab
This unlicensed template has limited function. You are free to unlock and modify licensed versions of these templates. See www.cvr-it.com for licensing information.
Instructions:
Before you enter any data, do the following:
- Determine the total cost of each project phase
- Determine the number of reporting periods that each project phase will last (e.g. 3 months)
- Determine (or guestimate) the dollar cost that will occur during each reporting period for each phase
To enter planned project values (note: all data entry cells are white):
1. Enter project name in the space provided
2. Enter reporting periods in cells D4 through AA4 (e.g. weeks, months or quarters as dates (shown) or month1, month2, etc.)
3. Enter cost of each project phase under Planned Phase Costs
4. Enter the phase cost planned for each Reporting Period in the white cells provided. (see Initiation and Planning for an example of how this is done). Leave unused cells blank.
Cells in column AB will be red until the total cost for all reporting periods in a phase equals the project phase cost.
5. Enter time unit of the project. This is "Months" in the example. This is used as a label on the chart.
6. Planned cost per reporting period display in the 'Budgeted Cost per Reporting Period" line
7. Planned Cumulative Cost displays in the "Cumulative Planned Cost" line
8. Enter Actual Costs per reporting period as the data become available. The cumulative actual cost will display in the
Cumulative Actual Cost line. It is normal for the last correct cumulative cost figure to repeat through all succeeding months. Do NOT delete these numbers!
9. Modify the graph in the Cumulative Cost Curve tab as explained on that sheet
When should you use this template:
- Use this template when you need a Cumulative Cost Curve and you have a good idea of how your costs will be broken
out over the course of your project.
- This template is useful for projects that last between 4 and 24 reporting periods and where dollar estimates of cost per reporting period are available.
- See companion document "CumulativeCostCurve_Dollars_SampleData.xls" to see what a completed project looks like.
Cumulative Cost Curve tab
Initial Setup
Once you have entered all of your Planned data in the Raw Data tab, do the following:
- Click once on the chart to select it and then click Chart on the toolbar
- Click Source Data and then Series
- Click Budgeted Cost and then in the Values box change "Raw data" to inlcude only the columns in which you have entered planning data.
For example, if your project will last 12 months you will have planned data in columns D through O, so the value for Raw Data should
be ='Raw Data'!$D$26:$O$26
Adding Actual Cost Data
As you add Actual Cost values, click once on the chart and then click Chart on the toolbar
- Click Source Data and then Series
- Click Actual Cost and then in the Values box change "Raw data" to inlcude the latest column in which you have Actual Cost data. In this -
the example we have Actual data for 3 months, so the last Actual data is in Column F. The value for Raw Data should
be ='Raw Data'!$D$30:$F$30
Note: this chart is easily added to a Word document. Just click on the chart, right click and Copy, then Paste into the Word document.
Template source: http://www.cvr-it.com